## milestones
Milestones | Date | Details
Eng debt + backlog defects + 10 % of SP4 epics | 20th Sep
60 % PRD readiness for M2 | 14th Sep | Load will be more on PM team (Scope closure + PRD for 40% of epics) in this milestones
60 % UX readiness for M2 | 14th Sep | Load will be more on UX team in this milestones
BC = 0 for M1 | 25th Sep
100 % PRD readiness for M2 | 18th Sep
100 % UX readiness for M2 | 18th Sep
Doc completion | 18th Sep
QA Sign-off | 18th Sep
STG Deploy & Sign-Off | 18th Sep
PROD deploy - M1 | 28th Sep
Eng completion - 40% of SP4 epics | 17th Oct
60 % PRD readiness for M3 | 12th Oct | PM team will do sign off on eng done epics + 30% epics for next milestones
60 % UX readiness for M3 | 12th Oct
Bug Bash (Internal) | 22nd Oct
100 % PRD readiness for M3 | 23rd Oct
100 % UX readiness for M3 | 23rd Oct
BC = 0 for M2 | 23rd Oct
Doc completion | 23rd Oct
QA Sign-off - M2 | 24th Oct
STG Deploy & Sign-Off - M2 | 25th Oct
PROD deploy - M2 | 26th Oct
Eng completion - 30% of SP4 epics + Spill over from M2 | 16th Nov
60 % PRD readiness for M4 | 9th Nov | PM team will complete sign-off + provide PRD for rest of the (20%) SP4 epics
60 % UX readiness for M4 | 9th Nov
BC = 0 for M3 | 19th Nov
100 % PRD readiness for M4 | 16th Nov
100 % UX readiness for M4 | 16th Nov
Doc completion | 20th Nov
QA Sign-off - M3 | 21st Nov
STG Deploy & Sign-Off - M3 | 22nd Nov
PROD deploy - M3 | 23rd Nov
Eng completion - 20% of SP4 epics + Spill over from M3 | 14th Dec | Eng team will focus on eng completion + testing effort will be more
PM sign-off on all eng done epics | 17th Dec | PM team will focus on sign-off + scope for V9
UX sign-off on all eng done epics | 17th Dec
V9 Scope discussion - draft | 26th Dec
BC = 0 for M4 | 18th Dec
Doc completion | 18th Dec
QA Sign-off - M4 | 19th Dec
STG Deploy & Sign-Off - M4 | 20th Dec
PROD deploy - M4 | 21st Dec
Spill over epics + hardening items | 28th Dec | Eng team will focus on defect fixing , close spill over items
Internal bug bash | 2nd Jan
Doc completion | 3rd Jan
Demo external teams | 3rd Jan
Bug bash external teams | 4th Jan
PRD readiness for V9 epics (30% of epics PRD progress > 60%) | 9th Jan
UX readiness for V9 epics (30% of epics) | 9th Jan
Sign-off from all teams including security, UX, PM | 3rd Jan
ZRB = 0 | 9th Jan
Code completion | 10th Jan
QA sign-off | 11th Jan
Buffer - 1 week
STG deployment | 17th Jan
PROD deployment | 18th Jan

## mails
Group | Mail
PM | pm@kony.com
UX | ux@kony.com
Doc | htshllwn@gmail.com
PRD | hitesh.lalwani04@gmail.com, hitesh.lalwani@kony.com
default | hitesh.lalwani@kony.com